## Procurement timetable
Procurement timetable | [13 empty] | 2021-10-25
FUT procurement identification number (FUT id nr) | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project (Extension part) | For participation in procurement registration is required with consulting brokers or qualification system | Only prequalified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for qualification of suppliers | Scheduled time for invitation to tender | Scheduled time for submission of tenders | Planned assignment start | Estimated cost SEK million | Link to further information | Procurement certainty | Procurement certainty
2651 | Construction and installation works - 7 stations (Sofia, Hammarby kanal, Gullmarsplan, Slakthuset, Sickla, Järla and Nacka C) | The contract comprises framework completions and installations for entrances, ticket halls, mezzanines, platforms, technical plan, service tunnel, ventilation shaft, fire shaft, etc. | Construction and installation | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | 2022-05 | 2022-09 | 2023-04 | 2024-05 | 600-700 |  | Yellow- relativly certain information
3717 | Rock excavation and civil works Arenastaden and Södra Hagalund | The assignment includes construction of a Access tunnel and preparation of an establishment area, rock shafts for tunnels, platform rooms, vertical shafts. Works with heavy steel and concrete framework for Arenastaden oand Södra Hagalund station and connecting tunnels to Hagastaden. Earth and foundation works for ticket halls. | Rock excavation and civil works | Arenastaden | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | 2021-11 | 2022-01 | 2022-02 | 2022-03 | > 1 000 | Green - information certain (within 3 months) | Yellow- relativly certain information
3727 | Construction and installation works Södra Hagalund and Arenastaden | The contracts comprise, among other things, ventilation and electric works, installation of escalators and elevators as well as pump stations. | Construction and installation | Arenastaden | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-Q2 | 2023-Q1 | 2023-Q2 | >1000 |  | Red - information uncertain
3742 | BEST assembly (Track-, Electrical-, Signal- and Telecommunication works) | The contract comprises assembly works for new rail installation. Rail and switch assembly, third-rail installation, low-voltage installations in rail tunnels, signals, etc. | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Arenastaden | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | 2022-Q4 | 2023-Q1 | 2023-Q3 | 2023-Q4 | 200-400 |  | Red - information uncertain | Red - information uncertain
3745 | Rectifier station Hälsingehöjden | The contract relates to the execution of extensive renovation and expansion of the existing rectifier station in Hälsingehöjden. | Building and installation works | Arenastaden | Precualification in TransQ is required | Yes 4.10.5 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2021-11-11 | 2022-02-01 | 20-30 |  | Green - information certain (within 3 months)
4715 | Concrete tunnel Veddesta | Design and build of concrete tunnel Veddesta | Rock excavation and civil works | Barkarby | Precualification in TransQ is required | Yes 9.4.3 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-03 | 2023-10 | 2023-12 | 40 |  | Red - information uncertain
4721 | Building and installation, Järfälla tunnel and stations | Including framework completion Installations (building incl. telecom) | Building and installation works | Barkarby | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | Finished | Finnished | 2021-11-08 | 500-1,000 |  | Green - information certain (within 3 months) | Red - information uncertain
4743 | Track, Electricity 400 volt, 3:rd rail, ducting | Järfällatunneln, BEST Track (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | Finished | Finnished | 2021-11-15 | 250-300 |  | Green - information certain (within 3 months) | Red - information uncertain
4744 | Signalling | BEST Signalling (Track-, Electrical-, Signal- and Telecommunication works). The contract includes signal installations Akalla - Barkaby. The signalling system is similar to the existing one on the blue metro, i.e. a Union&Switch system (relay-based system) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-12-01 | 2022-03-01 | 2022-05-01 | 25 |  | Yellow- relativly certain information | Red - information uncertain
4745 | Service and maintenace | Service and maintenance of temporary installations in facilities (plumbing etc.) | Maintenance | Barkarby | Precualification in TransQ is required | Yes | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-Q2 | 2022 Q3-Q4 | 2023 Q1 |  |  | Red - information uncertain
5710 | Connection track Farstagrenen | Rockexcavation of main cavern and connecting tunnels, concreteworks, servicetunnel, structure completion and installations in access- and service tunnel, connecting track and storage hall below ground. (Sprinklers, lighting, etc.) | Rock excavation and civil works and Installations works | Depot | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-03-18 | 2022-Q2 | 800-1000 |  | Green - information certain (within 3 months) | Red - information uncertain
5740 | BEST (Track, Electric power, Signal- and Telecommunication) | BEST Includes all new Track-, Electrical power, Signal , Telecommunication installations and channeling within exiting depot in Högdalen and new tunnel between existing depot and greenline (Farstabanan) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Depot | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2021-12-21 | 2022-06-01 | 100-300 |  | Green - information certain (within 3 months) | Red - information uncertain
7716 | Civil works Hammarby kanal | The contract comprises a rock shaft for rail tunnel and station areas at Sofia and Hammarby kanal. Concreting works and connecting earth works for ways up and entrances are also included. | Rock excavation and civil works | Södermalm | Precualification in TransQ is required | Yes 9.4.3 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2021-11-23 | 2022-Q1 | 500-1000 |  | Green - information certain (within 3 months) | Red - information uncertain
8715 | Civil works Järla | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Qualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-01-13 | 2022-april | 500-1000 |  | Green - information certain (within 3 months)
9712 | Civil works Sockenplan , stage 2 / Slakthusområdet | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-29 | 2022-04-15 | 2022-Q2 | 500-1000 |  | Green - information certain (within 3 months)
9713 | Civil works Sockenplan stage 3 | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract (Construction Contract) | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2028-Q3 | 2029-Q1 | 2029-Q2 | 50-100 |  | Red - information uncertain
15024 | Framework contract - apartment hotels | Temporary stay, Third-party apartment hotels. Refers to sub-area B, Arenastaden-Solna and sub-area H, Söder-Söderort | Service | All projects | N/A | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-18 | 2021-11-17 | 2021-12-01 |  |  | Green - information certain (within 3 months)
15025 | Framework contract- office hotels | Temporary stay, Third-party office hotels. Refers to sub-area E, Söder-Stockholm. | Service | All projects | N/A | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-18 | 2021-11-17 | 2021-12-01 |  |  | Green - information certain (within 3 months)
26310 | Coordination & logistics | Logistics, establishing sites, temporary instalations, mashines and equipment. Building work enviroment coorrdinator BAS-U. | Logistics | Nacka-southern suburbs | N/A |  | Design & Build Contract |  | 2022-09 | 2023-Q2 | 2023-Q4 | 500-700 |  | Red - information uncertain
26611 | Elevators and high capasity elevators | The contract includes 21 vertical elevators for all 7 stations on the Kungsträdgården - Nacka/söderort. The contract also includes 19 High capacity elevators for the stations Sofia, Nacka C and Gullmarsplan. | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.7 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-10 | 2023-03 | 2023-06 | 100-300 |  | Yellow- relativly certain information
26721 | Escalators Sickla - Nacka | The contract includes 10 escalators both < 30 meter and > 30 m for all 7 stations on the Kungsträdgården - Nacka/Söderort. | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.6 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-02-11 | 2022-05 | 2022-09 | 550-700 |  | Yellow- relativly certain information
26722 | Inclining elevators | The contract includes 12 inclining elevators for 7 stations for the Kungsträdgården - Nacka/Söderort | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.7 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-04 | 2022-10 | 2023-02 | 50-75 |  | Red - information uncertain
26723 | Escalators < 30 m | The contract includes 44 escalators < 30 meter for 7 stations for the Kungsträdgården - Nacka/Söderort | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.6 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-02-11 | 2022-05-27 | 2022-09 | 550-700 |  | Yellow- relativly certain information
26724 | Escalators > 30 m | The contract includes 18 Escalators > 30 meter for stations Hammarby kanal, Slakthusområdet, Sickla, Nacka C på sträckan Kungsträdgården - Nacka/söderort | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.6 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-02-11 | 2022-05-27 | 2022-09 | 250-350 |  | Yellow- relativly certain information
26726 | Electricity, Telecom and Controll | Electricity 400V, Telecom, and BMS for 7 stations for the Kungsträdgården - Nacka/Söderort route | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-08 | 2023-02 | 2023-05 | 700-800 |  | Yellow- relativly certain information
26727 | HVAC including ventilation | Plumbing, pump stations and ventilation for 7 stations for Kungsträdgården - Nacka/Söderort | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.4.9 | Design & Build Contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-09 | 2023-03 | 2023-06 | 500-1000 |  | Yellow- relativly certain information
267110 | Track, walking path, Third rail 750V Kungsträdgården-Hammarby kanal and Sofia-Sockenplan | Track work, troughs, Thrid rail 750 V for Kungsträdgården - Hammarby Kanal and Sofia- Sockenplan. The contract includes among other, tracks, power cable, cable trays and walkway along tracks | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | 2022-Q2 | 2022-Q2 | 2022-Q3 | 2022-Q4 | 200-300 |  | Green - information certain (within 3 months) | Red - information uncertain
267120 | Track, walking path and Third rail 750V Hammarby kanal-Nacka | Track work, troughs, Thrid rail 750 V for Hammarby Kanal - Nacka. he contract includes among other, tracks, power cable, cable trays and walkway along tracks. | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | 2022-Q2 | 2022-Q2 | 2022-Q3 | 2022-Q4 | 200-300 |  | Green - information certain (within 3 months)
267200 | Electricity 400V, Telecom | The contract covers both electrisity (e.g. lighting, power supply in the tunnels and 1kv system in the service tunnel) as well as Telecommunication (e.g. opticafiber infrastructure, cameras, radio and antenna system) and Prefabricated technical houses for Kungsträdgården - Nacka and Sofia - Sockenplan. | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | 2022 Q4 | 2022 Q4 | 2023 Q2 | 2023 Q3 | 150-250 |  | Yellow- relativly certain information | Red - information uncertain
267310 | Signalling | The contract includes signal installations for the Kungsträdgården - Nacka and Sofia-Sockenplan route. The signalling system is similar to the existing one on the blue metro, i.e. a Union&Switch system | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | 2023 Q2 | 2023 Q2 | 2023 Q4 | 2024 Q1 | 250-350 |  | Yellow- relativly certain information | Red - information uncertain
267400 | Mouting ducting and cable laying | Mouting ducting och cabling for Kungsträdgården - Nacka and Sofia- Sockenplan. The contract includes the installation of cable ladders and cable consoles in both track and service tunnels, as well as EST-kable i tunnels. | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract (Construction Contract) | 2023 Q1 | 2023 Q1 | 2023 Q3 | 2023 Q4 | 150-250 |  | Yellow- relativly certain information | Red - information uncertain
| Signal equipment strategic | For the blue metro (Barkarby+Söder) | Other | All projects | Precualification in TransQ is required | Yes | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-12-22 | 2022-03 | 2022-05 |  |  | Red - information uncertain
| Signal equipment not strategic | For the blue metro (Barkarby+Söder) | Other | All projects | Precualification in TransQ is required | Yes | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-12-22 | 2022-03 | 2022-05 |  |  | Red - information uncertain
| Avsjö design (Assignment 1) Station layout | Station layout | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-27 | 2021-12-21 | 2022-01-27 |  |  | Green - information certain (within 3 months)
| Älvsjö design (Assignment 2) Engeneering | Engeneering | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-27 | 2021-12-21 | 2022-01-27 |  |  | Green - information certain (within 3 months)
| Älvsjö design (Assignment 3) Railway plan | Railway plan | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-27 | 2021-12-08 | 2022-01-17 |  |  | Green - information certain (within 3 months)
| Design Älvsjö (Assignment 4) Environmental permit and hydrogeology | Environmental permit and hydrogeology | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-10-27 | 2021-12-08 | 2022-01-17 |  |  | Green - information certain (within 3 months)
| Design Älvsjö (Assignment 5) Station design | Station design for 3 stations | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-04-01 | 2021-05-13 | 2022-06-15 |  |  | Yellow- relativly certain information
| Design Älvsjö (Assignment 6) Station design | Station design for 3 stations | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-04-01 | 2021-05-13 | 2022-06-15 |  |  | Yellow- relativly certain information
| Design Älvsjö (Assignment 7) Tunnel and track design | Preparation/production of system documents for the tunnel / BEST | Service | Älvsjö |  | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-04-01 | 2021-05-13 | 2022-06-15 |  |  | Yellow- relativly certain information
| Design Älvsjö | Design of construction documents, preparatory work for the metro project to Älvsjö | Service | Älvsjö | Registration with consultant broker is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-Q3 | 2023-Q4 | 2024-Q1 |  |  | Red - information uncertain
| Framework agreement Printing services | The assignment refers to printing services such as e.g. roll-ups, newsletters, sidewalk poster posters, etc. | Service | All projects | N/A | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-11 | 2021-12 | 2021-12 | <4 |  | Yellow- relativly certain information

## template
Uppdrag | Projekt | Registrering hos konsultmäkl | Transq | Entreprenadform | Kostnad | Upphandlare | Sannolikhet
Framework agreement | Barkarby | Precualification in TransQ is required | Yes 9.1.0 | Build only contract | 0-5 | Anders Karnestrand | Green - information certain (within 3 months)
Preparatory work | Arenastaden | Registration with consultant broker i required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | 5-20 | Cecilia Tennfors | Red - information uncertain
| All projects | No registration or prequalification is required | Yes 9.1.1 |  |  |  | Yellow- relativly certain information
Access tunnel works | Depå |  | Yes 9.4.6 | Combo | 20-50 | Pia Lindberg-Nedby | Data not available
Rock excavation and civil works | Nacka |  | Yes 9.4.7 | Service | 50-100 | Peter Malmsten
Building and installation works | Söder |  | Yes 9.4.3 |  | 100-300
Installation | Söderort |  | No |  | 300-500
BEST (Track-, Electrical-, Signal- and Telecommunication works) | Södermalm |  |  |  | 500-1 000
Other | Älvsjö |  |  |  | > 1 000
Combination | All projects |  |  |  | Data missing