## Upphandlingstidplan
Procurement timetable - Extended Metro in Stockholm
Update 2022-04-11
Identification number for Administration for Extended Metro in Stockholm | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project | Participation in procurement requires registration with consulting brokers or in qualification system | Only prequlified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for qualification of suppliers | Scheduled time for invitation to tender | Time for submission of tender | Planned contract start | Estimated cost MSEK | Procurement certainty
2651 | Construction works 7 stations (Sofia, Hammarby kanal, Gullmarsplan, Slakthuset, Sickla, Järla and Nacka C) | The contract involves non-load-bearing elements of 7 new metro stations along the Blue Line in Nacka and Söderort. The scope is all station spaces, technical rooms, and concrete and asphalt works in the service tunnel. These works include light walling, doors and glazed partitions, ironworks, suspended ceilings, floor coverings, all wall and ceiling finishes, and collaboration in integrating the artistic decoration. The contract also includes the coordination of other contractors' planning and work within the work area. | Construction | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022 - September | 2023-April | 2023-June | 600-700 | Yellow-relativly certain information
3726 | Vertical transport Solna Escalators > 30 m | The contract comprises 22 escalators ( 9 of them is climbing more than 30 metres in height) for the stations Södra Hagalund and Arenastaden. | Installation works | Arenastaden | Prequalification in TransQ is required | Yes TransQ cod 4.2.6 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-August | 2022-November | 2022-December | < 500
3727 | Construction, installation, telecom, control (BITS) | The contract includes construction and installation works for Södra Hagalund and Arenastaden and tele/control installations for the entire Yellow Line. The contract includes, among other things, non-load-bearing elements such as light walling, wall panels, ironworks, glazed partitions, suspended ceilings, flooring and other surface finishing. Installations for heating, water, sewage, sprinklers, ventilation, lighting, electricity/tele/control, elevators, escalators for a complete station. | Construction and installation | Arenastaden | Prequalification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-February | 2023-Q3 | 2023-Q4 | >1 000 | Red-information uncertain
3742 | BEST assembly (Track, Electrical, Signal and Telecomunication works) | The contract comprises assembly work for a new track system. Track and switch installation, third track installation, low-voltage installations in rail tunnels, signals, etc. | BEST (Track, Electrical, Signal and Telecomunication works) | Arenastaden | Prequalification in TransQ is required | Yes TransQ cod 9.1.1 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-Q4 | 2024-Q2 | 2024-Q4 | 200-400 | Red-information uncertain
4715 | Concrete tunnel Veddesta | Concrete tunnel | Civil works | Barkarby | Prequalification in TransQ is required | Yes TransQ cod 9.4.3 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-Q3 | 2024-Q2 | 2024-Q3 | 40 | Red-information uncertain
4716 | Concrete wall Runway (civil works) | Concrete wall between rail tunnel and temporary access tunnel. | Civil works | Barkarby | Prequalification in TransQ is required | Yes TransQ cod 9.4.3 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2024-Q2 | 2024-Q4 | 2025-Q2 | 10 | Red-information uncertain
4717 | Backfilling Runway (ground work) | Backfilling of temporary access tunnel between concrete wall (contract 4716) and ground surface and restoration work on ground surface. | Civil works | Barkarby | Prequalification in TransQ is required | Yes | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2024-Q2 | 2024-Q4 | 2025-Q2 | 10 | Red-information uncertain
4744 | Signalling works | The contract comprises signalling installations for the Akalla-Barkarby section. The signalling system is similar to the existing one on the Blue Line, that is, a Union&Switch system (relay-based system). | BEST (Track, Electrical, Signal and Telecomunication works) | Barkarby | Prequalification in TransQ is required | Yes TransQ cod 9.1.2 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-Jun | 2022-August | 25 | Green-information certain (within 3 months)
4772 | Service and maintenance | Operation and maintenance of temporary installations in facilities (HVAC, etc.) | Maintenance | Barkarby | Prequalification in TransQ is required | Ja | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023 - Q1 | 2023-Q2 | 2023-Q3 | 10 | Red-informRed-information uncertaination uncertain
4781 | Restoration works 4781 | Miscellaneous restoration works, including worksites and complementary work not included in other contracts. | Civil works | Barkarby | Prequalification in TransQ is required | Ja | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2025-Q2 | 2025-Q3 | 2025-Q3 | 10 | Red-information uncertain
5710 | Connecting track Farstagrenen | Rockexcavation of main cavern and connecting tunnels, concreteworks, servicetunnel, structure completion and installations in access- and service tunnel, connecting track and storage hall below ground. (Sprinklers, lighting, etc.) | Rock excavation and civil works & construction and installation | Depot | Prequalification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Finished | Finished | 2022-Jun | 800-1000 | Green-information certain (within 3 months)
8715 | Civil works Järla | The assignment includes excavation for the rail tunnel, station spaces, concrete works and associated ground works. | Rock excavation and civil works | Nacka | Qualification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Finished | Finished | 2022-April | 500-1000 | Green-information certain (within 3 months)
9712 | Civil works Sockenplan stage 2 and Slakthuset area | Construction work: The assignment includes excavation for the rail tunnel, station spaces, concrete works (incl. planning and re-locating roads), geo structures (incl. planning) and associated ground works. | Rock excavation and civil works | Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-04-29 | 2022-Jun | 500-1000 | Green-information certain (within 3 months)
9713 | Civil works Sockenplan stage 3 | Construction work: The assignment includes concrete cuttings, ground and road works, grouting, earth and rock excavation, etc. | Rock excavation and civil works | Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2028-Q3 | 2029-Q1 | 2029-Q2 | 50-100 | Red-information uncertain
26310 | Coordination & Logistics | Coordination & Logistics Provide service to other contractors. Construction services Establishing sites Temporary installations General services Logistics centre Transport BAS-U (OHS Coordinator Construction) | Logistics | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 4.1.99, 4.13.1, 4.13.3, 4.13.5, 4.14.1, 4.14.99, 8.3.1, 8.6.3, 8.6.99, 8.8.8 eller 8.12.16 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-November | 2023-Q3 | 2023-Q4 | 500-700 | Yellow-relativly certain information
26610 | Vertical transport - Elevators and high-capasity elevators | The contract comprises 21 vertical elevators for all 7 stations on the Kungsträdgården - Nacka/Söderort section. The contract comprises 19 high-capasity elevators for the stations Sofia, Gullmarsplan and Nacka C on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 4.2.7 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-October | 2023-Q1 | 2023-Q2 | 100-300 | Yellow-relativly certain information
26622 | Vertical transport - Escalators Sickla - Nacka | The contract comprises 10 escalators (climbing both less than and more than 30 metres in height) for all 7 stations on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 4.2.6 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-August | 2022-November | 550-700 | Green-information certain (within 3 months)
26612 | Vertical transport - Inclined elevators | The contract comprises 12 inclined elevators for all 7 stations on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 4.2.7 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022 - October | 2023-Q1 | 2023-Q2 | 100 | Yellow-relativly certain information
26620 | Vertical transport - Escalators < 30 m | The contract comprises 44 escalators (climbing less than 30 metres in height) for all 7 stations on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 4.2.6 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-August | 2022-November | 550-700 | Green-information certain (within 3 months)
26621 | Vertical transport - Escalators > 30 m | The contract comprises 18 escalators (climbing more than 30 metres in height) for the stations Hammarby kanal, Slakthuset, Sickla and Nacka C on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 4.2.6 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | Ongoing procurement | 2022-August | 2022-November | 250-350 | Green-information certain (within 3 months)
26640 | Electricity/telecom/control | The contract comprises electricity, telecommunications, control and lighting for all 7 stations on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.4.1 – 9.4.9 or 9.4.99 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-September | 2023-Q1 | 2023-Q2 | 700-800 | Yellow-relativly certain information
26650 | HVAC | The contract comprises HVAC including fire and tunnel ventilation for all 7 stations and the line on the Kungsträdgården - Nacka/Söderort section. | Installation works | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.4.9 | Design & build contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-September | 2023-Q1 | 2023-Q2 | 500-1 000 | Yellow-relativly certain information
267110 | Track, walking paths and third rail | Kungsträdgården - Hammarby kanal & Sofia - Sockeplan sections. The contract comprises tracks, third rail, disconnectors, walkway along tracks and cable trays along tracks. | BEST (Track, Electrical, Signal and Telecomunication works) | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.1.1 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-September | 2023-Februari | 2023-May | 200-300 | Yellow-relativly certain information
267120 | Track, walking paths and third rail | Hammarby Kanal - Nacka section. The contract comprises tracks, third rail, disconnectors, walkway along tracks and cable trays along tracks. | BEST (Track, Electrical, Signal andTelecomunication works) | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.1.1 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-September | 2023-Februari | 2023-May | 200-300 | Yellow-relativly certain information
267200 | Electricity 400 V, Tele | The contract comprises 400 V installations (e.g. lighting, power outlets) as well as telecom installations (e.g. fibre network, camera installations, radio system, IP network) in rail and service tunnels. The contract is for the Kungsträdgården - Nacka and Sofia - Sockenplan sections. | BEST (Track, Electrical, Signal and Telecomunication works) | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.1.1 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-Q1 | 2023-Q3 | 2023-Q4 | 150-250 | Yellow-relativly certain information
267310 | Signalling | The contract comprises signal installations for the Kungsträdgården - Nacka and Sofia - Sockenplan sections. The signalling system is similar to the existing one on the Blue Line, that is, a Union&Switch system (relay-based system). | BEST (Track, Electrical, Signal and Telecomunication works) | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.1.2 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-Q2 | 2023-Q4 | 2024-Q1 | 250-350 | Yellow-relativly certain information
267400 | Duct installation and cable routing | The contract comprises the installation of cable ladders and cable brackets in rail and service tunnels, as well as the procurement and routing of EST (electrical, signal and telecom) cables. The contract is for the Kungsträdgården - Nacka and Sofia - Sockenplan sections. | BEST (Track, Electrical, Signal and Telecomunication works) | Nacka-Söderort | Prequalification in TransQ is required | Yes TransQ cod 9.1.1 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-October | 2023-April | 2023-Q3 | 150-250 | Yellow-relativly certain information
26832 | Strategic signalling equipment Blue Line | For the Blue Line (Barkarby+South) | Other, Delivery of goods | Common | Prequalification in TransQ is required | Ja | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-May | 2022-Q3 | 2022-Q3 | 20-50 | Red-information uncertain
26833 | Strategic signalling equipment - impedance bonds | For the Blue Line (Barkarby+South) | Other Delivery of goods | Common | Prequalification in TransQ is required | Ja | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022 - May | 2022-Q3 | 2022-Q3 | 100-300 | Red-information uncertain
26834 | Strategic signalling equipment - signals | For the Blue Line (Barkarby+South) | Other Delivery of goods | Common | Prequalification in TransQ is required | Ja | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022 - May | 2022-Q3 | 2022-Q3 | 5-20 | Red-information uncertain
26835 | Strategic signalling equipment - signal mounts | For the Blue Line (Barkarby+South) | Other Delivery of goods | Common | Prequalification in TransQ is required | Ja | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022 - May | 2022-Q3 | 2022-Q3 | 0-5 | Red-information uncertain
| Station design 3 stations Alvsjö (assignment 5) | Station design for 3 stations | Service | Älvsjö | Registration in WFQ is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022 - April | 2022-June | 2022-August |  | Yellow-relativly certain information
| Station design 3 stations Alvsjö (assignment 6) | Station design for 3 stations | Service | Älvsjö | Registration in WFQ is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-April | 2022-June | 2022-August |  | Yellow-relativly certain information
| Tunnel/ BEST (Track, Electrical, Signal and Telecom) design Alvsjö (assignment 7) | Preparation/production of system documents for the tunnel / BEST | Service | Älvsjö | Registration in WFQ is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-April | 2022-June | 2022-August |  | Yellow-relativly certain information
| Design Älvsjö | Design of construction documents, preparatory work for the metro project to Älvsjö | Service | Älvsjö | Registration in WFQ is required | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2023-Q3 | 2023-Q4 | 2024-Q1 |  | Red-information uncertain
| Framework agreement Contaminated excavated materials | The contract comprises the handling of contaminated excavated materials from the expansion of the metro. The transport of contaminated excavated materials from construction sites to the handling facility is not included in this procurement. | Service | common | No registration or prequalification is required. | N/A | N/A | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2022-April | 2022-Q2 | 2022-Q3 | 20-50 | Yellow-relativly certain information