## Procurement plan
Procurement timetable - Extended Metro in Stockholm
Update 2024-03-11
Identification number for Administration for Extended Metro in Stockholm | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project | Participation in procurement requires registration with consulting brokers or in qualification system | Only prequlified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for invitation to tender | Time for submission of tender | Planned contract start | Estimated cost MSEK | Procurement certainty
3742 | BEST assembly (Track, Electrical, Signal and Telecomunication works) | The contract comprises assembly work for a new track system. Track and switch installation, third track installation, low-voltage installations in rail tunnels, signals, etc. | BEST (Track, Electrical, Signal and Telecomunication works) | Arenastaden | Prequalification in TransQ is required | Yes, at least in one of the following TransQ codes 9.1.1, 9.1.2, 9.1.4, 9.4.4, 9.4.5 and/or 9.4.8 | Execution contract | 2024-Sep | 2024-Dec | 2025-May/Jun | 200-400 MSEK | Green-information certain (within 3 months)
3722 | Construction and installationworks, Södra Hagalund | The contract includes construction and installation work within one (1) station, Södra Hagalund, as well as in the connecting service tunnel. The stairs start from the middle of the platform room up to the entrance level. Construction and installation work refers to frame completion with lightweight walls, brick walls, wall panels, forging, glass sections, floors, suspended ceilings and other surface layers. VS, air treatment, sprinklers, electricity and reserve power as well as lighting, transport vertical elevator and inclined elevator etc. This contract includes VA works and pumping stations for the Södra Hagalund, Arenastaden and Hagastaden stations. | Construction- and installationworks | Arenastaden | Prequalification in TransQ is required | YesTransQ code 9.4 | Execution contract | Ongoing | Ongoing | 2024-Sept | 400-450 MSEK | Green-information certain (within 3 months)
3723 | Construction and installationworks, Arenastaden | The contract includes construction and installation work within one (1) station, Arenastaden, and in the connecting service tunnel. The stairs start from the middle of the platform room up to the entrance level. Construction and installation work refers to frame completion with lightweight walls, brick walls, wall panels, forging, glass sections, floors, suspended ceilings and other surface layers. VS, air treatment, sprinklers, electricity and reserve power as well as lighting, transport vertical elevator and inclined elevator etc. | Construction- and installationworks | Arenastaden | Prequalification in TransQ is required | Yes,TransQ code 9.4 | Execution contract | Ongoing | 2024-Oct | 2024-Nov | 350-400 MSEK | Green-information certain (within 3 months)
3728 | Overall tele and controll | This procurement includes contracting regarding overall telecommunication and control work for the stations Södra Hagalund, Arenastaden, Hagastaden, in the entire stretch of the service tunnel and in technical spaces located in the entire stretch of the service tunnel. Telecommunications and control work refers to telecommunications, control and monitoring as well as integration and testing against superior systems. | Installationworks | Arenastaden | Prequalification in TransQ is required | Yes, TransQ code 9.4.4 and/or 9.4.5 | Execution contract | Ongoing | 2024-Oct | 2025-Jan | 150-200 MSEK | Green-information certain (within 3 months)
| System assignment, Depot | The assignment includes the preparation of a system document regarding the tunnel and BEST for the connecting tracks between the line and the depot area, including the necessary shafts. The assignment also includes the system documentation of a new depot that contains the depot functions needed for the line as well as the production of calculation documents for assignment feasibility. | Consultant | Metro tol Älvsjö | Magnit registration is required | N/A | ABK Assignment | Ongoing | 2024-sept | 2024-oct | 100 MSEK | Green-information certain (within 3 months)
| Design assignment BH 1 - Stations Fridhemsplan and Liljeholmen | The scope of the assignment includes detailed design and design of tender documents for contractor procurement. | Consultant | Metro to Älvsjö | Magnit registration is required | N/A | ABK Assignment | 2024-May | 2024-Aug | 2024-Nov/Dec | 200 MSEK | Green-information certain (within 3 months)
| Design assignment BH 2 - Stations Årstafältet, Östbergahöjden and Älvsjö | The scope of the assignment includes detailed design and design of tender documents for contractor procurement. | Consultant | Metro to Älvsjö | Magnit registration is required | N/A | ABK Assignment | 2024-May | 2024-Aug | 2024-Oct | 200 MSEK | Green-information certain (within 3 months)
| Design assignment BH 3 - TBM/Tunnelling and station Årstaberg | The scope of the assignment includes detailed design and design of tender documents for contractor procurement. | Consultant | Metro to Älvsjö | Magnit registration is required | N/A | ABK Assignment | 2024-May | 2024-Aug | 2024-Nov/Dec | 150 MSEK | Green-information certain (within 3 months)
| Client support organisation for engineering services related to procurement of complete integrated traffic system solution, Yellow line. | The engineering organisation shall supply relevant general technical support and more specific e.g. develop functional requirements and other technical descriptions as part of tender documents enabling procurement of complete integrated traffic system solution, Yellow line. Possibly will also options for serices during the tender as well as during execution be included. | Consultant | Metro to Älvsjö | Magnit registration is required | N/A | ABK Assignment | 2024-Sept | 2024-Okt | 2024-Nov | >20 MSEK | Green-information certain (within 3 months)
| Traffic System, as a complete integrated solution, Yellow line. | Complete Traffic System Solution, automation level GoA4 for Yellow line. Turnkey basis based on functional requirements. Including e.g. but not limited to, Rolling stock, Traffic control, signalling, Traction power, Track system, Communication systems. Full system integration responsibility. | D&B Electro- mechanical works | Metro to Älvsjö | Prequalification in TransQ is required (not decided) |  | Execution contract | 2025-Dec | 2026-Nov | 2027 - June | ca 2 000 MSEK | Röd - uppgifter ej säkra
| Rock- and contruction work - access tunnels and station for Yellow line | A package (package 2) of several procurements that includes a number of rock and construction contracts for two access tunnels, geotechnical work at two stations and vertical shafts including station space for the stations: Älvsjö, Östbergahöjden, Årstafältet and Liljeholmen | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | Yes | Execution contract | 2025-June -- 2027-Apr | 2025-Sept -- 2027-Aug | 2025-Dec -- 2027-Sept | Mellan 50 - 450 MSEK, totalt ca 1 750 MSEK | Röd - uppgifter ej säkra
| TBM tunneling construction worksand station Årstaberg. | This contract (package 3) includes TBM tunneling works, twinn tunnel in parallell for Yellow line from Älvsjö to Fridhemsplan. The contract also includes the station Årstaberg. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required (not decided) |  | D&B with selective parts build. | 2025-Dec | 2026-Oct | 2027-Feb | ca 4 500 MSEK | Röd - uppgifter ej säkra
| Rock and civil construction works, station Fridhemsplan | The contract (package 5) including rock- and civil works construction for the station Fridhemsplan, both accesstunnel and station area. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | Yes | Execution contract, Cost plus | 2025-Nov | 2026-March | 2026-May | ca 600 MSEK | Röd - uppgifter ej säkra