## Procurement plan
Procurement timetable - Extended Metro in Stockholm
Update 2024-12-16
Identification number for Administration for Extended Metro in Stockholm | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project | Participation in procurement requires registration with consulting brokers or in qualification system | Only prequlified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for invitation to tender | Time for submission of tender | Planned contract start | Estimated cost MSEK | Procurement certainty
3742 | BEST assembly (Track, Electrical, Signal and Telecomunication works) | The contract comprises assembly work for a new track system. Track and switch installation, third track installation, low-voltage installations in rail tunnels, signals, etc. | BEST (Track, Electrical, Signal and Telecomunication works) | Arenastaden | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.4, 9.4.5 and 9.4.8 | Execution contract | Done | Done | 2025-May/Jun | 200-400 MSEK | Green-information certain (within 3 months)
| Client Support Organization for the Investigation of a Metro to Bromma Parkstad | A city development project is planned at Bromma Airport once aviation operations cease. This creates an opportunity to enhance public transportation, including the development of a subway. The assignment involves preparing a localization study for a subway to the future Bromma Parkstad during 2025 and 2026. | Consultant | Metro till Bromma Parkstad | Magnit registration is required | N/A | ABK Assignment | Done | Done | 2025-May/Jun | <40 MSEK | Green-information certain (within 3 months)
77121 | Access Tunnel Älvsjö IP | The procurement includes sheet piling, earth excavation, and tunnel excavation. The tunnel is approximately 200 meters long. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | TransQ code 9.4.3 | Execution contract | 2025-Sept | 2025-Nov | 2026-Jan | 90-130 MSEK | Yellow - relatively reliable information
77132 | Geotechnical Structure Årstafältet | The procurement includes geotechnical work for a vertical elevator shaft, consisting of a permanent sheet pile structure. Earth excavation and concrete work are also included. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.1-9.4.9 eller 9.4.99 | Design-Build Contract | 2025-Sept | 2025-Dec | 2026-Mars | 50-100 MSEK | Yellow - relatively reliable information
77122 | Access Tunnel Årstaberg | The procurement includes sheet piling, earth excavation, and tunnel excavation. The tunnel is approximately 500 meters long. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | TransQ code 9.4.3 | Execution contract | 2025-Dec | 2026-Mars | 2026-May | 130-170 MSEK | Yellow - relatively reliable information
77214 | Rock and Construction Works at Östbergahöjden Station | The procurement includes underground rock and civil construction works. The rock excavation will be carried out through a drop shaft. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2026-Jan | 2026-Apr | 2026-Jun | 360-460 MSEK | Yellow - relatively reliable information
77211 | Rock and civil construction works at Fridhemsplan Station | The contract including rock- and civil works construction for the station Fridhemsplan, both accesstunnel and station area. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 eller 9.4.99 | Execution contract | 2026-Mar | 2026-July | 2026-Sept | 530-630 MSEK | Yellow - relatively reliable information
| Traffic System, as a complete integrated solution, Yellow line. | Complete Traffic System Solution, automation level GoA4 for Yellow line. Turnkey basis based on functional requirements. Including e.g. but not limited to, Rolling stock, Traffic control, signalling, Traction power, Track system, Communication systems. Full system integration responsibility. | D&B Electro- mechanical works | Metro to Älvsjö | No | N/A | Assignment ("Turnkey") | 2026-Aug | 2028-Jan | 2028 - June | 2000-4000 MSEK | Yellow - relatively reliable information
77141 | Depot Pit | Depot Pit in Älvsjö Industrial Area includes earthworks, rockworks, demolition, and sheet piling. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2026-Apr | 2026-Aug | 2026-Okt | 120-160 MSEK | Gul - relativt säkra uppgifter
77142 | Tunneling works (incl.TBM) and station Årstaberg | This contract (package 3) includes TBM tunneling works, twinn tunnel in parallell for Yellow line from Älvsjö to Fridhemsplan. The contract also includes the station Årstaberg. | Civil works | Metro to Älvsjö | No | N/A | D&B with selective parts build. | 2026-Jan | 2027-Jan | 2027-July | 4400-4800 MSEK | Gul - relativt säkra uppgifter
| Geotechnical Structure Liljeholmen | The procurement includes geotechnical work for a vertical elevator shaft, consisting of a permanent sheet pile structure. Earth excavation and concrete work are also included. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Design-Build Contract | 2026-June | 2026-Sept | 2027-Jan | 40-60 MSEK | Gul - relativt säkra uppgifter
| Rock and Construction Works at Liljeholmen Station | This procurement includes a rock and civil works contract for Liljeholmen Station, covering both the access tunnel and station space. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 eller 9.4.99 | Execution contract | 2026-Okt | 2027-Jan | 2027-Mars | 280-380 MSEK | Gul - relativt säkra uppgifter
| Rock and Construction Works at Älvsjö Station | The procurement includes underground rock and civil works. The work will commence from the access tunnel. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2027-Feb | 2027-May | 2027-Sept | 370-470 MSEK | Red - uncertain information
| Depot (includes multiple procurements) | Construction of the depot includes depot buildings, connecting tracks, and associated tunnels. It will be divided into three procurements : South of the Excavation Pit, Excavation Pit and Buildings and Installations. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.1 eller 9.4.99 | Execution and Design-Build Contract contract | From 2027-Jun | From 2027-Nov | From 2028 | 2000-2500 MSEK | Red - uncertain information
| Rock and Construction Works at Årstafältet Station | The procurement includes underground rock and civil works. The rock excavation will be carried out through a drop shaft. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2027-Apr | 2027-Aug | 2027-Okt | 350-450 MSEK | Red - uncertain information
| Construction and Installation (includes multiple procurements) | Construction and installation contracts for six stations. These will be divided into multiple procurements/contracts. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 eller 9.4.8 | Design-Build Contract | From 2028 | From 2028 | From 2028 | 2800-3300 MSEK | Red - uncertain information