## Procurement plan
Procurement timetable - Extended Metro in Stockholm
Update 2025-12
Identification number for Administration for Extended Metro in Stockholm | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project | Participation in procurement requires registration with consulting brokers or in qualification system | Only prequlified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for invitation to tender | Time for submission of tender | Planned contract start | Estimated cost MSEK | Procurement certainty
4715 | Concrete tunnel Vedesta | The project comprises the construction of a concrete tunnel approximately 100 metres long in Veddesta, connecting to a previously built access tunnel. The works mainly involve concrete construction, but also include earthworks such as excavation and backfilling, foundation work using steel pipe piles, and installation of cable trays.The procurement also includes a concrete plug, removal of sheet piling, and reinstatement works for a previously constructed construction tunnel at Landningsbanan that will not be required during the operational phase. | Civil works | Metro to Barkarby | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 and/or 9.4.99 | Execution contract | 2026-juni | 2026-nov | 2027-april | 90-100 MSEK | Yellow - relatively reliable information
97058 | Civil Works Finishing South – Part 1 | The scope includes the execution of various types of works along the entire extension of the metro to Nacka and Söderort, both underground and above ground. | Civil works | Metro to Nacka-söderort | Prequalification in TransQ is required | One of the TransQ codes: 9.4.2, 9.4.3, 9.4.6, 9.4.7 och/eller 9.4.99 | Execution contract | Completed | 2026-Jan | 2026-Feb | 50-100 MSEK | Green-information certain (within 3 months)
77051 | Preparatory work, Östbergahöjden Station | The work includes preparations for upcoming contracts. It includes preparation of the establishment area, relocation of optical cables, and utility works for connection of electricity and water/sewage. | Entreprenad | Metro to Älvsjö | Prekvalificering krävs i TransQ | En av TransQ koder: 9.4.6, 9.4.7 och/eller 9.4.8 | Execution contract | Completed | Completed | 2026-feb | 5-20 MSEK | Grön - säker (inom 3 månader)
77012 | Preparatory work, Access tunnel Fridhemsplan | The work includes preparations for upcoming contracts. It includes preparation of the establishment area and utility works for connection of electricity and water/sewage. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.6, 9.4.7 or 9.4.8 | Execution contract | 2026-feb | 2026-april | 2026-maj | 5-20 MSEK | Green-information certain (within 3 months)
77063 | Preparatory work, Starting pit TBM Älvsjö | The work includes preparations for upcoming contracts. It includes preparation of the establishment area and utility works for connection of electricity, water/sewage and optical cables. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.6, 9.4.7 or 9.4.8 | Execution contract | 2026-feb | 2026-april | 2026-maj | 0-5 MSEK | Green-information certain (within 3 months)
77121 | Access Tunnel Älvsjö IP | The procurement includes sheet piling, earth excavation, and tunnel excavation. The tunnel is approximately 200 meters long. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | TransQ code 9.4.3 | Execution contract | Completed | Completed | 2026-Jan | 90-130 MSEK | Green-information certain (within 3 months)
77122 | Access Tunnel Årstaberg | The procurement includes sheet piling, earth excavation, and tunnel excavation. The tunnel is approximately 500 meters long. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | TransQ code 9.4.3 | Execution contract | 2025-Dec | 2026-Mars | 2026-June | 130-170 MSEK | Green-information certain (within 3 months)
77132 | Geotechnical Structure Årstafältet | The procurement includes geotechnical work for a vertical elevator shaft, consisting of a permanent sheet pile structure. Earth excavation and concrete work are also included. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.1-9.4.9 eller 9.4.99 | Design-Build Contract | Completed | 2026- Jan | 2026-Mars | 50-100 MSEK | Green-information certain (within 3 months)
77131 | Geotechnical Structure Liljeholmen | The procurement includes geotechnical work for a vertical elevator shaft, consisting of a permanent sheet pile structure. Earth excavation and concrete work are also included. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Design-Build Contract | 2026-Oct | 2027-Feb | 2027-June | 40-60 MSEK | Yellow - relatively reliable information
77141 | Depot Pit | Depot Pit in Älvsjö Industrial Area includes earthworks, rockworks, demolition, and sheet piling. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2026-mar | 2026-jun | 2026-okt | 120-160 MSEK | Green-information certain (within 3 months)
77111 | Rock and civil construction works at Fridhemsplan Station | The contract including rock- and civil works construction for the station Fridhemsplan, both accesstunnel and station area. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 eller 9.4.99 | Execution contract (time and materials) | 2026-Mar | 2026-July | 2026-Sept | 530-630 MSEK | Green-information certain (within 3 months)
77112 | Rock and Construction Works at Liljeholmen Station | This procurement includes a rock and civil works contract for Liljeholmen Station, covering both the access tunnel and station space. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 eller 9.4.99 | Execution contract | 2026-Oct | 2027-Jan | 2027-Mars | 280-380 MSEK | Red - uncertain information
77113 | Rock and Construction Works at Årstafältet Station | The procurement includes underground rock and civil works. The rock excavation will be carried out through a drop shaft. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2027-Apr | 2027-Aug | 2027-Oct | 350-450 MSEK | Red - uncertain information
77114 | Rock and Construction Works at Östbergahöjden Station | The procurement includes underground rock and civil construction works. The rock excavation will be carried out through a drop shaft. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 eller 9.4.99 | Execution contract | 2026 Q1 | 2026 Q2 | 2026 Q2 | 360-460 MSEK | Red - uncertain information
77115 | Rock and Construction Works at Älvsjö Station | The procurement includes underground rock and civil works. The work will commence from the access tunnel. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 eller 9.4.99 | Execution contract | 2027-Feb | 2027-June | 2027-Sept | 370-470 MSEK | Red - uncertain information
77142 | Tunneling works (incl.TBM) and station Årstaberg | This contract (package 3) includes TBM tunneling works, twinn tunnel in parallell for Yellow line from Älvsjö to Fridhemsplan. The contract also includes the station Årstaberg. | Civil works | Metro to Älvsjö | No | N/A | D&B with selective parts build. | 2026 Q1 | 2027 Q1 | 2027 Q3 | 4400-4800 MSEK | Red - uncertain information
77211 77212 77213 77214 77215 77216 | Construction and Installation (includes multiple procurements) | Construction and installation contracts for six stations. These will be divided into multiple procurements/contracts. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 eller 9.4.8 | Design-Build Contract | From 2028 | From 2028 | From 2028 | 2800-3300 MSEK | Red - uncertain information
73221 | Traffic System, as a complete integrated solution, Yellow line. | Performance-based procurement of a fully integrated transport system solution for the Yellow Line, including systems for driverless trains (GoA-4), encompassing rolling stock, traffic control including signalling systems, electrification, communication, and other subsystems. The procurement also includes, to some extent, maintenance, system operations, and trafic operations. | D&B Electro- mechanical works | Metro to Älvsjö | No | N/A | Assignment ("Turnkey") | 2026-Dec | 2028-June | 2029-Jan | 3000-5000 MSEK | Red - uncertain information
| Depot (includes multiple procurements) | Construction of the depot includes depot buildings, connecting tracks, and associated tunnels. It will be divided into three procurements : South of the Excavation Pit, Excavation Pit and Buildings and Installations. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.1 eller 9.4.99 | Execution and Design-Build Contract contract | 2027-Q3 | 2027-Q4 | 2028-Q1 | 2000-2500 MSEK | Red - uncertain information
| Mass handling, Excavated Rock | Reception, handling (e.g., through crushing), storage, and sale of rock masses at a location provided by the client within the City of Stockholm. | Service | Metro to Älvsjö | No | N/A | N/A | 2027-Q4 | 2028-Q1 | 2028-Q3 | - | Red - uncertain information
| Art for the Yellow Line | The administration intends to procure artistic design for six (6) stations between Fridhemsplan and Älvsjö. The stations include Älvsjö (including façade), Östbergahöjden (including façade), Årstafältet, Årstaberg (including façade), Liljeholmen (including façade), and Fridhemsplan. | Service | Metro to Älvsjö | No | N/A | N/A | 2026-Q3 | 2027-Q2 | 2027-Q3 | 30-40 MSEK | Red - uncertain information
N/A | Organization for measurement of groundwater levels and settlement movements | The consultancy assignment concerns measurement of groundwater levels and settlements during the project implementation. Management of measurement points is also included. The assignment period is from January 2026 to December 2030, with five optional years (1+1…). Scope: approximately ten positions. The assignment replaces the current ongoing assignment in this area | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | Completed | Completed | 2026-01-12 | 40-50 MSEK | Green-information certain (within 3 months)
N/A | Inspection and Measurement Organization, Yellow Line | The consultancy assignment concerns inspection of properties/facilities and measurement of vibration and noise before, during, and after the construction phase of the Metro extension to Älvsjö. The assignment period is from February 2026 to December 2033, with a maximum of four optional years (1+1…) | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | Completed | Completed | 2026-02-02 | 40-50 MSEK | Green-information certain (within 3 months)
N/A | Organization for construction management – geodetic surveying | Consultancy assignment regarding measurement services within the contracts; the assignment covers the entire construction period. Scope: one to four positions | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | 2025-11-03 | 2025-12-05 | 2026-02-02 | 40-50 MSEK | Green-information certain (within 3 months)
N/A | Construction Management Organization Assignment 1* | Contract division for the Yellow Line will be defined at a later stage. The assignment includes the following disciplines: rock, concrete, groundworks, and other (e.g., TFI). | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | 2026-feb | 2026-mar | 2026-apr | To be completed later, not yet finalized | Yellow - relatively reliable information
N/A | Construction Management Organization Assignment 2* | Contract division for the Yellow Line will be defined at a later stage. The assignment includes the following disciplines: TBM (tunnel boring machine), rock, concrete, groundworks, and other (e.g., TFI). | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | 2026-feb | 2026-mar | 2026-apr | To be completed later, not yet finalized | Yellow - relatively reliable information