## Procurement plan
Procurement timetable - Extended Metro in Stockholm
Update 2026-09-01
Identification number for Administration for Extended Metro in Stockholm | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project | Participation in procurement requires registration with consulting brokers or in qualification system | Only prequalified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for invitation to tender | Time for submission of tender | Planned contract start | Estimated cost MSEK | Procurement certainty
4715 | Concrete tunnel Vedesta, concrete plug and refill by Barkabyfield | The procurement includes the construction of an approximately 100-metre-long concrete tunnel in Veddesta, including associated earthworks and foundation works, as well as the reinstatement of parts of an existing access tunnel. | Civil works | Metro to Barkarby | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 and/or 9.4.99 | Execution contract | 2026-Q4 | 2027-Q1 | 2027-Q2 | 90-100 MSEK | Red - information not secure
77131 | Geotechnical Structure Liljeholmen | The procurement includes geotechnical work for a vertical elevator shaft, consisting of a permanent sheet pile structure. Earth excavation and concrete work are also included. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 or 9.4.99 | Design-Build Contract | 2026-Dec | 2027-april | 2027-July | 40-60 MSEK | Yellow - relatively reliable information
77141 | Starting Pit TBM Älvsjö | The procurement includes earthworks, rock excavation, demolition works, and sheet piling works for the depot excavation in the Älvsjö industrial area. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.7 or 9.4.99 | Execution contract | Completed | Completed | 2026-Oct | 120-160 MSEK | Green-information certain (within 3 months)
77111 | Rock and civil construction works at Fridhemsplan Station | The contract contains rock- and civil works construction for the station Fridhemsplan, including both access tunnel and station area in connection to the exsisting metro station Fridhemsplan | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 or 9.4.99 | Execution contract (time and materials) | Completed | 2026-Oct | 2026 -Dec | 530-630 MSEK | Green-information certain (within 3 months)
77112 | Rock and Construction Works at Liljeholmen Station | This procurement includes a rock and civil works contract for Liljeholmen Station, covering both the access tunnel and station space. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 or 9.4.99 | Execution contract | 2026-Dec | 2027-April | 2027-July | 280-380 MSEK | Red - information not secure
77114 | Rock and civil construction works at Östberjahöjden Station (Sinking Schaft) | The procurement includes a vertical schaft down to stationlevel for the Östbergahöjden station | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.3, 9.4.7 or 9.4.99 | Execution contract | Completed | 2026-Sept | 2026-Nov | 100-200 MSEK | Green-information certain (within 3 months)
77181 | Traverse Station Östbergahöjden | The procurement includes delivery and installation of a traverse to the clients establishment in Östbergahöjden. The delivery also includes service and maintenance. | Vara | Metro to Älvsjö | No | N/A | N/A | Completed | 2026-Aug | 2026-Sept | 5-20 MSEK | Green-information certain (within 3 months)
77142 | TBM and southern stations | This procuremnt inlcudes rock and civil works construction with two TMB- machines för the entire linke from Älvsjö to Fridhemsplan. The contracts also inludes cavern and shaft for the following stations: Älvsjö, Östbergahöjden, Årstafältet and Årstaberg. | Civil works | Metro to Älvsjö | No | N/A | Design Build contract frame including some works where the Client is responsible for the design | Completed | 2027-Q4 | 2028- Q1 | 5300-6100 MSEK | Green-information certain (within 3 months)
77211 | Construction and Installation Contract – Fridhemsplan Station | The procurement covers all parts of the station building for Fridhemsplan Station, including foundations, certain geotechnical structures, groundworks and landscaping, structural framework, structural completion, interior and exterior finishes, and building services installations. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 or 9.4.8 | Design-Build Contract | From 2028 and onwards | From 2028 and onwards | From 2028 and onwards | 450-550 MSEK | Red - uncertain information
77212 | Construction and Installation Contract – Liljeholmen Station | The procurement covers all parts of the station building for Liljeholmen Station, including foundations, certain geotechnical structures, groundworks and landscaping, structural framework, structural completion, interior and exterior finishes, and building services installations. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 or 9.4.8 | Design-Build Contract | From 2028 and onwards | From 2028 and onwards | From 2028 and onwards | 450-550 MSEK | Red - uncertain information
77213/77214 | Construction and Installation Contract – Årstafältet and Östbergahöjden Stations | Årstafältet and Östbergahöjden Stations will be procured as a single contract. The procurement covers all parts of the station buildings for Årstafältet and Östbergahöjden, including foundations, certain geotechnical structures, groundworks and landscaping, structural framework, structural completion, interior and exterior finishes, and building services installations. Excavation works at Årstafältet and Östbergahöjden will be carried out using the cut-and-cover excavation method. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 or 9.4.8 | Design-Build Contract | From 2028 and onwards | From 2028 and onwards | From 2028 and onwards | 450-550 MSEK | Red - uncertain information
77215 | Construction and Installation Contract – Älvsjö Station (potential combined bidding with Årstaberg Station) | The procurement covers all parts of the station building for Älvsjö Station, including foundations, certain geotechnical structures, groundworks and landscaping, structural framework, structural completion, interior and exterior finishes, and building services installations. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 or 9.4.8 | Design-Build Contract | From 2028 and onwards | From 2028 and onwards | From 2028 and onwards | 450-550 MSEK | Red - uncertain information
77216 | Construction and Installation Contract – Årstaberg Station (potential combined bidding with Älvsjö Station) | The procurement covers all parts of the station building for Årstaberg Station, including foundations, certain geotechnical structures, groundworks and landscaping, structural framework, structural completion, interior and exterior finishes, and building services installations. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.1.1, 9.1.2, 9.1.4, 9.4.1, 9.4.4, 9.4.5 or 9.4.8 | Design-Build Contract | From 2028 and onwards | From 2028 and onwards | From 2028 and onwards | 450-550 MSEK | Red - uncertain information
77241 | Elevators and escalators | The procurement includes 30 high-capacity elevators to all stations except Fridhemsplan. 2 inclined elevators to Fridhemsplan station. 12 platform elevators to all stations. 2 elevators to the ticket hall – park side to the stations Älvsjö and Liljeholmen. All stations on the yellow line include 12 platform escalators and 3 long escalators for station Fridhemsplan | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 4.2.7 or 4.2.6 | Design-Build Contract | 2027 Q3 | 2027 Q4 | 2030 Q2 | 300-350Msek | Red - uncertain information
73221 | Complete integrated traffis system | Functional procurement of a complete integrated traffic system solution, which includes a system for autonomous trains (GoA-4) including vehicles, traffic control including signaling systems, electrification, communication and other subsystems. The procurement also includes maintenance of the traffic system and traffic operation to some extent. | Service incl. Goods and contracts | Metro to Älvsjö | No | N/A | Assignment ("Turnkey") | 2027-Q3 | 2028-Q4 | 2029-Q2 | 3000-5000 MSEK | Red - uncertain information
| Depot | This package of procurements includes depot buildings, connecting tracks with associated tunnels. Will be divided into three contracts, South of the shaft pit, Shaft pit and construction as well as Buildning and installation. | Civil works | Metro to Älvsjö | Prequalification in TransQ is required | One of the TransQ codes: 9.4.1 or 9.4.99 | Execution and Design-Build Contract | 2027-Q3 | 2027-Q4 | 2028-Q1 | 2000-2500 MSEK | Red - uncertain information
77191 | Mass handling, Excavated Rock | Receiving, handling (e.g., through crushing), storage, and sale of rock masses at a location provided by the client within the City of Stockholm. | Service | Metro to Älvsjö | No | N/A | N/A | 2027-Q1 | 2027-Q2 | 2027-Q3 |  | Yellow - relatively reliable information
N/A | Art for the Yellow Line | The procurement includes artistic design for six (6) stations on the section between Fridhemsplan and Älvsjö. The stations are Älvsjö (including the façade), Östbergahöjden (including the façade), Årstafältet, Årstaberg (including the façade), Liljeholmen (including the façade), and Fridhemsplan. | Service | Metro to Älvsjö | No | N/A | N/A | 2026-Q3 | 2027-Q2 | 2027-Q3 | 30-40 MSEK | Yellow - relatively reliable information
N/A | Construction Management Organization Assignment 1 | The assignment includes the following disciplines: rock, concrete, groundworks, and other (e.g., TFI). | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | 2026-Sept | 2026-Oct | 2026-Nov | 200-300 MSEK | Yellow - relatively reliable information
N/A | Construction Management Organization Assignment 2 | The assignment includes the following disciplines: TBM (tunnel boring machine), rock, concrete, groundworks, and other (e.g., TFI). | Service | Metro to Älvsjö | Registration required with consultancy broker | N/A | N/A | 2026-Sept | 2026-Oct | 2026-Nov | 200-300 MSEK | Yellow - relatively reliable information